## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | self | 2026-02-05 | Incorrect IVR call flow mapping during analysis | Sprint 1 | Backend Team | Logical | Reviewed VXML flow and corrected mapping | 2026-02-06 | Closed | Resolved
2 | self | 2026-02-08 | Mismatch in integration requirements documentation | Sprint 1 | Backend Team | Standards | Updated requirement specification as per format | 2026-02-09 | Closed | Validated
3 | self | 2026-02-18 | API not receiving request from IVR system | Sprint 1 | Backend Team | Logical | Fixed API endpoint configuration | 2026-02-18 | Closed | Working
4 | self | 2026-02-20 | Incorrect API response format | Sprint 1 | Backend Team | Standards | Modified JSON response structure | 2026-02-21 | Closed | Verified
5 | self | 2026-02-24 | API not handling invalid input properly | Sprint 1 | Backend Team | Logical | Implemented input validation logic | 2026-02-25 | Closed | Stable
6 | self | 2026-03-05 | Speech recognition not detecting user input | Sprint 1 | Backend Team | Logical | Improved speech configuration | 2026-03-05 | Closed | Working
7 | self | 2026-03-08 | Incorrect conversational response generated | Sprint 1 | Backend Team | Logical | Updated dialogue flow logic | 2026-03-09 | Closed | Corrected
8 | self | 2026-03-20 | System issue during end-to-end testing | Sprint 1 | Backend Team | Maintainability | Refactored integration logic and retested system | 2026-03-21 | Closed | Stable

## Sheet2
Logical
User Interface
Maintainability
Standards
Others